## Slide 1: THE LIGHT PARK 2026
Creative Playbook & Strategic Roadmap

## Slide 2: Table of Contents
Executive Summary
Project Timeline Overview
February 2026 - Foundation & Character Development
March 2026 - Content Creation & Digital Platforms
April 2026 - Integration & Finalization
May 2026 - Public Launch & Production
June 2026 - Community Engagement
Concept Visualizations

## Slide 3
Executive Summary
Strategic Vision for 2026 Season

## Slide 4: Mission Statement
THE LIGHT PARK 2026 season represents a transformative leap forward in holiday entertainment
Expanding to 8 venues across multiple locations
Introducing DJ Polar Ice and Pixel Penguin character-driven experiences
Integrating cutting-edge technology and immersive storytelling
Creating unforgettable holiday memories for all guests

## Slide 5: Key Objectives
✓ Venue Expansion: Launch new Oklahoma City park location
✓ Character Integration: Fully integrate DJ Polar Ice and Pixel Penguin
✓ Experience Enhancement: Redesign tent experiences with digital screens
✓ Digital Transformation: Launch mobile app and YouTube channel
✓ Content Creation: Develop new audio sequences and theme songs

## Slide 6: Brand Cohesion
Strict adherence to THE LIGHT PARK brand identity
Signature color palette: Primary Purple, Ice Blue, Accent Purple, Gnome Red
Character universe consistency across all touchpoints
Professional, polished presentation for stakeholder review
Cohesive brand presence across all materials and experiences

## Slide 7
Project Timeline Overview
February - June 2026

## Slide 8: Phase Overview - Gantt Chart
February: Character Development & Venue Design
• DJ Polar Ice avatar development
• Pixel Penguin concept design
• Oklahoma City park layout
• Tent enhancement concepts
March: Content Creation & Digital Launch
• YouTube channel setup
• Festival map prototypes
• Mobile app development
• Audio track production

## Slide 9: Key Milestones - Linear Timeline
February 2026: Foundation & Character Development
✓ DJ Polar Ice avatar photo shoot complete
✓ Pixel Penguin designs finalized
✓ OKC park layout approved
March 2026: Content & Digital Platform Launch
✓ YouTube channel created (private)
✓ Festival map prototypes developed
✓ Mobile app beta testing begins
April 2026: Integration & Finalization
✓ Bumper tracks integrated
✓ Festival maps finalized
✓ Branding approved

## Slide 10
February 2026
Foundation Building & Character Development

## Slide 11: DJ Polar Ice Avatar Development
HIGH PRIORITY - Mascot Photo Shoot & Facial Animation
• Schedule professional photographer with mascot experience
• Capture multiple angles and expressions
• Create animation library for marketing and shows
HIGH PRIORITY - Lip-Sync Modeling & Gesture Animation
• Create phoneme library (English/Spanish)
• Design gesture animations
• Test animation smoothness
HIGH PRIORITY - Voice Creation
• Audition bilingual voice actors
• Record core phrases
• Integrate with show control systems

## Slide 12: Pixel Penguin & Venue Design
HIGH PRIORITY - Pixel Penguin Character Design
• Develop 5-7 concept variations
• Focus on mischievous, tech-savvy traits
• Create final 3D model
HIGH PRIORITY - Oklahoma City Park Layout
• Conduct site survey and measurement
• Design traffic flow patterns
• Map emergency exits and safety compliance
• Position concession tent and merchandise areas
MEDIUM PRIORITY - Themed Area Development
• Audit existing prop inventory
• Design layouts for returning venues

## Slide 13: Tent Experience Enhancement
HIGH PRIORITY - Tent Redesign
• Design 16' tall pixel screens for entrances
• Create custom rolling shelving units
• Design rolling cart for popcorn machines
• Develop standardized tent layout template
HIGH PRIORITY - Merchandising Strategy
• Display DJ Polar Ice plushies
• Electric lemonade, cake pops, cotton candy
• Generate AI concept images
MEDIUM PRIORITY - Marketing Assets Organization
• Create centralized digital asset library
• Establish file naming conventions

## Slide 14
March 2026
Content Creation & Digital Platform Development

## Slide 15: Digital Platforms Launch
MEDIUM PRIORITY - YouTube Channel
• Create channel with proper branding
• Design channel art and thumbnails
• Upload initial content for review
• Conduct brand consistency audit
HIGH PRIORITY - Festival Map Prototypes
• Design site-specific maps for all 8 venues
• Include DJ Polar Ice story teaser
• Create sponsorship placement zones
• Begin sponsor outreach

## Slide 16: Mobile App & Content Creation
HIGH PRIORITY - Mobile App Development
• Provide branding materials to developer
• Review UI/UX designs
• Test beta versions
• Ensure brand consistency
MEDIUM PRIORITY - Storybook Concept
• Write DJ Polar Ice origin story
• Create teaser excerpts
• Develop character dialogue
HIGH PRIORITY - Theme Song/Jingle
• Compose signature audio branding
• Create instrumental and vocal versions
• Integrate into marketing and shows

## Slide 17: Audio & Sequence Production
MEDIUM PRIORITY - Character Dialog
• Write bumper track scripts
• Develop bilingual content
• Add personality to show experience
HIGH PRIORITY - New Audio Track Production
• Create minimum 3 new sequences
• Select current music tracks
• Design light synchronization patterns
MEDIUM PRIORITY - Digital Character Images
• Create pixel screen-optimized graphics
• Design phoneme animations
• Test display quality
HIGH PRIORITY - xLights Layout Completion
• Map sequences to all 8 venues
• Test HTML upload scripts
• Enable mid-season updates

## Slide 18
April 2026
Integration & Finalization Phase

## Slide 19: Integration & Finalization
HIGH PRIORITY - Bumper Track Integration
• Import all tracks into xLights
• Add theme song backgrounds
• Maintain light animation during transitions
HIGH PRIORITY - Site Layout Finalization
• Complete all 8 festival maps
• Obtain domestic printing quotes
• Solicit overseas printing quotes
• Make final printing decision
HIGH PRIORITY - Branding Finalization
• Comprehensive graphic design review
• Ensure brand cohesion
• Obtain stakeholder approvals

## Slide 20: App Finalization
HIGH PRIORITY - Mobile App Completion
• Confirm all use cases
• Test ticketing system integration
• Conduct user acceptance testing
• Prepare for app store submission
HIGH PRIORITY - Quality Assurance
• Test all features across devices
• Verify brand alignment
• Validate user experience
• Final bug fixes and improvements

## Slide 21
May 2026
Public Launch & Production Phase

## Slide 22: Social Media Launch
HIGH PRIORITY - Multi-Platform Launch
• Begin content release on YouTube, TikTok, Instagram
• Post teaser content and character reveals
• Monitor engagement metrics daily
• Adjust strategy based on performance
Key Success Metrics
• Viewer engagement and watch time
• Social media follower growth
• Content sharing and virality
• Brand awareness and recognition

## Slide 23: Production & Early Bird Sales
HIGH PRIORITY - Tent Improvement Production
• Finalize concession enhancement designs
• Begin manufacturing pixel screens
• Procurement of rolling shelving units
• Fabrication of rolling carts
MEDIUM PRIORITY - Early Bird Sales Planning
• Define promotional packages
• Establish pricing tiers
• Create marketing materials
• Set launch dates
HIGH PRIORITY - Sequence Upload Process
• Upload new sequences to all props
• Update existing content
• Test playback quality
• Continue through July

## Slide 24
June 2026
Community Engagement & Pre-Season Preparation

## Slide 25: Community Engagement
MEDIUM PRIORITY - Community Outreach
• Contact local schools for spirit nights
• Develop school partnership packages
• Approach businesses for group sales
• Create promotional materials
MEDIUM PRIORITY - App Audio Content
• Develop pre-arrival audio experience
• Create queue entertainment content
• Explore sponsorship opportunities
• Integrate into mobile app
Partnership Goals
• Build community relationships
• Increase group ticket sales
• Enhance brand local presence

## Slide 26
Concept Visualizations
AI-Generated Images for Tent Enhancements

## Slide 27: Tent Enhancement Concepts
🎪 Grand Entrance Design
• 16' tall pixel screens at tent leg entrances
• DJ Polar Ice content displays
• Immersive arrival experience
🛍️ Merchandise Display
• Custom rolling shelving units
• DJ Polar Ice plushies showcase
• Electric lemonade, cake pops, cotton candy
• Organized, visually appealing arrangement
🍿 Concession Experience
• Rolling cart for popcorn machines
• Themed branding design
• Efficient service flow
• Standardized across venues

## Slide 28: Ready for 2026!
THE LIGHT PARK - Creating Magical Holiday Experiences